## Risk Register
Risk Register
Risk | Probability (%) | Impact | Mitigate | Monitored | Assigned To (Management) | Number of Hours | Risk Exposure(RE)
Database Connectivity | 100% | severe | proper session conectivity,Hibernate jars included | 2019-07-11 | Charanpreet Singh (TL) | 4 | 4 | Severe = 5
Group member sick | 50% | High | All group members should have updated information about all the aspects of the project | 2019-07-11 | Charanpreet Singh (TL) | 3 | 1.5 | High = 4
Git hub code conflicts | 75% | Moderate | Pull and Push requests should be made properly | 2019-07-11 | Charanpreet Singh (TL) | 5 | 3.75 | Moderate = 3
Data Validation | 50% | High | Proper data validation done for each input | 2019-07-11 | Harpreet Kaur | 8 | 4 | Low = 2
Proper app connectivity | 25% | Low | Checking all the Jframes are properly linked | 2019-07-10 | Charanpreet Singh (TL) | 6 | 1.5 | Unlikely = 1
Conflict between Group Members | 25% | Low | Listen to each and every group Member,Mutual Understanding | every Day | Charanpreet Singh (TL) | 1 | 0.25

## ESRI_MAPINFO_SHEET (hidden)
DO NOT EDIT
For Esri use only